## Gantt Chart
|  | PROJECT TITLE |  | CS401 Project
Members | Abbreviation | WBS NUMBER | TASK TITLE | [5 empty] | DUE DATE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
Jacob Le Nguyen | Jacob | [8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
Harrison Fisher | Harry | [8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Daniel Ochoa Morales | Daniel | 1 | Requirement Development Phase | Jacob | Harry | Daniel | Nick | Brian | 2022-03-02
Nicholas Khine | Nick | 1.1 | SRS Document | ✔️ | ✔️ | ✔️ | ✔️ |  | 2022-02-21 | bar: WEEK 1 M to WEEK 3 F
Brian Le | Brian | 1.2 | Team Meetings Doc |  | ✔️ | ✔️ |  |  | 2022-02-21 | bar: WEEK 1 M to WEEK 3 F
|  | 1.3 | Project Schedule Doc | ✔️ |  |  |  |  | 2022-02-21 | bar: WEEK 1 M to WEEK 3 F
|  | 2 | Design Development Phase | [5 empty] | 2022-04-03
2.1
|  | 3 | Application and Programming Phase | [5 empty] | 2022-05-04
3.1
|  | 4 | Testing and Maitenence | [5 empty] | N/A
4.1