## Gantt Chart
|  | PROJECT TITLE |  | CS401 Project
Members | Abbreviation | WBS NUMBER | TASK TITLE | [5 empty] | DUE DATE | PHASE ONE | [19 empty] | PHASE TWO | [19 empty] | PHASE THREE
Jacob Le Nguyen | Jacob |  |  | WORK DONE BY WHO | [5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
Harrison Fisher | Harry | [8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Daniel Ochoa Morales | Daniel | 1 | Requirement Development Phase | Jacob | Harry | Daniel | Nick | Brian | 2022-03-02
Nicholas Khine | Nick | 1.1 | SRS Document | ✔️ | ✔️ | ✔️ | ✔️ |  |  | WEEK 1 F: SRS Doc Being Developed
Brian Le | Brian | 1.2 | Team Meetings Doc |  | ✔️ | ✔️ |  |  |  | WEEK 2 R: Team Meeting Doc
|  | 1.3 | Project Schedule Doc | ✔️ | [5 empty] | WEEK 3 T: Project Schedule Doc
|  | 2 | Design Development Phase | [5 empty] | 2022-04-06
|  | 2.1 | UML Project Design Graphs | ✔️ | ✔️ | ✔️ | ✔️ | ✔️ |  | WEEK 6 F: UML Design Graphs
|  | 2.2 | Design Specification Document | ✔️ | ✔️ | ✔️ | ✔️ |  |  | WEEK 6 F: Design Specification Document
|  | 3 | Application and Programming Phase | [5 empty] | 2022-05-04
|  | 3.1 | IT Window / Person Class / Server Thread Class | ✔️ | [5 empty] | WEEK 10 W: Implimentation and Application
|  | 3.2 | Client Class / Chat Window / Login Window / Conversation Class |  | ✔️ | bar: WEEK 9 W to WEEK 12 F
|  | 3.3 | Server Classes / Message Class / Person Class / Conversation Class |  |  | ✔️ | bar: WEEK 9 W to WEEK 12 F
|  | 3.4 | Server Classes / Person Class / Server Thread Class |  |  |  | ✔️ | bar: WEEK 9 W to WEEK 12 F
|  | 3.5 | Log class |  |  |  |  | ✔️ | bar: WEEK 9 W to WEEK 12 F
|  | 4 | Testing and Maitenence | [5 empty] | 2022-05-04
|  | 4.1 | Testing (No maintinence done and everyone tests their own classes they created) | ✔️ | ✔️ | ✔️ | ✔️ | ✔️ |  | WEEK 12 R: Testing